## Slide 1: Costing the Covid 19 vaccination programme in the Ministry of Health Seychelles.
Dr. Shobha Hajarnis.
Consultant
Ministry of Health Secretariat

## Slide 2: Background Information
The Republic of Seychelles consists of 115 islands and has a total population of about 98,000 people. Only the islands of Mahe, Praslin and La Digue have significant permanent populations. Around 27,000 people in that population are below the age of 18 years.
To achieve COVID-19 herd immunity through vaccination, science suggests that between 60 and 70% of the population need to be vaccinated
Therefore, Seychelles calculated its target population for vaccination at around 70,000 people since all COVID-19 vaccines available at the conceptualization of the deployment plan were indicated for people above the age of 18 years.

## Slide 3: Vaccine Policy Decisions
Most of the COVID 19 vaccines are given in two doses about 28 days apart.
Seychelles did not join the Covax facility programme initiated by WHO because of the high cost of embarking on the COVAX facility was weighed against other alternatives and other needs both in the health sector and other sectors.
Initially Seychelles received the support of some of its international partners All together Seychelles received 81,000 doses of Sinopharm vaccine and 59,000 doses of Covishield (AstraZeneca) vaccine.
The Ministry of Health decided to vaccinate the population age 18 to 60 years with the SINOPHARM vaccine and people above the age of 60 years and those people having chronic medical conditions with the COVISHIELD (Oxford AstraZeneca) vaccine.

## Slide 4: Development of Covid 19 vaccination deployment plan
To assist countries to prepare for vaccine introduction, WHO published its Guidance on Developing a National Deployment and Vaccination Plan for COVID-19 vaccines. Seychelles established the National Technical Working Group (NTWG) in early December to develop the COVID-19 vaccination rollout plan. Seven thematic groups were created:
Procurement of vaccines
Supply and cold chain management
Prioritisation of target groups and surveillance.

## Slide 5
Human resources and training
Risk communication/Social Mobilisation/ Health promotion
Adverse events following immunisation (AEFI) and vaccine safety issues.
Monitoring and evaluation.

## Slide 6
This COVID-19 vaccine deployment plan outlined the processes and activities involved to assure safe delivery of vaccines and ancillary items to protect the vulnerable population during the current COVID 19 pandemic.
It addressed vaccination strategies, management and organization, communication and information, human resources and security, public information, pandemic vaccine deployment operations (Supply Chain Processes) and collection of medical waste required to execute a thorough and high-quality vaccination campaign.

## Slide 7: Vaccine deployment
Prioritisation for vaccination was based on published evidence highlighting those most at risk of getting COVID infection: Vaccination will target the following groups in order of priority:
Health care workers
Frontline workers- e.g. Police officers, Public utilities workers, Armed forces, Port and Airport workers.
Key leaders and decision makers.
Persons above the age of 60 years.
Persons having comorbid conditions.
Persons above the age of 18 years.

## Slide 8: Management and Organisation.
The overall management Covid 19- 2021 vaccine deployment and subsequent campaign is going to be managed by the EPI unit under the direction of NTWG of the Ministry of health
The development of a communication strategy is being done in consultation with the COVID 19 vaccine introduction committee. (National technical working group)- SCR.50,000/-
A Vaccine Deployment Training/Planning Workshop was held for all staff involved in the process before the commencement of the vaccination campaign.SCR.15,000/-
Stationaries for internal printing- 400,000/-
Total Budget required- SCR. 465,000/-

## Slide 9: Communication and Public Information
During any major immunisation campaign communication and information management is critical to the success of the campaign. Sharing the accurate information about the vaccine, target groups, adverse events following immunization, vaccine arrival details and cold chain requirements is essential.
In our health care setting, mobile phones, Intranet, Internet and land lines are the preferred form of the communication
A brief information sheet for all health professionals covering all aspects of the Covid 19 vaccine cold chain requirement is essential to ensure that the standardised information is available amongst health care workers at any given time.

## Slide 10: Continued
Public awareness and information is the key to the success of any public health campaign. It is essential to inform the public of the availability of vaccine, Prioritisation of target population, adverse effects etc.
In addition to this, funding is needed for a large public awareness campaign such as utilising television, radio and print Medias, and will run for a total of 4 weeks during the vaccination campaign.
Total funding required is, SCR. 800,000/-

## Slide 11: Human resources for campaign
All nurses involved in the vaccination campaign had undergone the training before starting the campaign.. 1. These nurses are also responsible for data reporting, AEFI reporting and other concerns on the field.
Eight vaccination teams are deployed for the campaign, seven for Mahé and one team for Praslin and La Digue. Each team is having a dedicated medical officer, who has remained on site during the vaccination. 102 Nurses and allied health professionals and eight doctors made up the vaccination teams. The vaccination campaign is planned for 6 months.
Total Budget required – SCR 22, 000,000/- ( includes remuneration, per diem and displacement cost and salaries of health professionals dedicated to Campaign activities)

## Slide 12: Logistics for Vaccination campaign.
The national vaccination stock management system is well developed for the routine childhood immunisation programme. The COVID 19 vaccination campaign will utilise the existing system.
Distribution of vaccine stock is going to be tracked via vaccine stock registers that can identify the location of batches of the vaccine.
Equipment Required to Vaccinate Target Population with vaccination cold chain is critical. Vaccine transport and storage equipment in all forms needs to be procured and deployed, wherever is needed.
Total Budget required- SCR. 750,000/- (Includes, Refrigerated container, Fuel for transport)

## Slide 13: Supply chain and cold chain management
The cold chain capacity needs to be increased in order to store COVID 19 vaccine.
Vaccine carriers, thermometers and freeze tags and safety boxes and vaccine refrigerators are being procured before the arrival of the vaccines.
For vaccines that are not dispatched as pre-filled syringes, auto-disable syringes are also being procured.
Total budget required- 420,000/- (Includes vaccine fridges, safety boxes, Auto- disabled syringes and thermometers)

## Slide 14: Adverse events following immunisation and vaccine safety.
Seychelles has a well-functioning monitoring system for adverse events following routine immunisation. (AEFI).
Any AEFI suspected by a doctor or a nurse during the COVID 19 vaccination campaign is notified to the EPI programme manager and is investigated by the AEFI committee as and when required.
All AEFI committee members are trained on AEFI caused by Covid 19 vaccine.
Total Budget required- SCR. 23,000/- (AEFI members need to conduct supervisory visits to various health facilities.)

## Slide 15: Collection of medical waste resulting from the COVID 19 vaccine vaccination campaign
Currently there are two functioning incinerators in the Ministry of Health based at Seychelles hospital on Mahé and Baie St. Anne hospital at Praslin which are used to incinerate all medical waste.
Additional funding is required to incinerate medical waste generated by the vaccination campaign.
Total Funding required – SCR. 100,000/-

## Slide 16: Monitoring and Evaluation
Monitoring and Evaluation of the COVID 19 vaccine campaign is going to be a continues process throughout and after the completion of the campaign. Statisticians and data entry clerks will be collecting ,cleaning and analysing the data.
vaccination data records are kept on a daily basis and tally for the management.
A final campaign report will be produced and will be published at the end of the campaign.
Total budget required to publish the report- SCR 5,000/-

## Slide 17
The budget outlined includes the cost of vaccines. It makes provision for eventual booster doses for the whole population, should this be necessary, but does not include provisions for vaccination of persons below the age of 18 years.
Total cost of procuring vaccine-SCR30,271,000/-

## Slide 18
Activities | Cost in Seychelles Rupees
Procurement of Covid 19 vaccines to be used in the vaccination campaign. | 30,271,000
Cost of potential booster doses of Covishield and Sinopharm vaccine should it be needed in future | 17,640,000
Management and organisation | 465,000
Communication and public information | 800,000
Human resources for vaccination campaign (includes remuneration, per diems, displacement costs, salaries of Health professionals) | 22,000,000
Logistics for campaign | 750,000
Supply chain management | 420,000
AEFI and vaccine safety | 23,000
Disposal of medical waste | 100,000
Monitoring and evaluation report | 5,000
Total budget required | 72,474,000/-
Cost in US $ (one US$- SCR.21/-) | 3,451,143/-
Proposed Budget for 2021 Vaccination Campaign